AFTER ACTION REPORT WMS Cutover Weekend Harbor Point Logistics · Event 9–12 Oct 2026 · Review 14 Oct 2026

| FACILITATOR | PARTICIPANTS | CLASSIFICATION | STATUS |
| --- | --- | --- | --- |
| Dana Whitcomb, PMO | 14 (ops, IT, docks, vendor) | Internal · no-blame review | Actions open: 6 |

| 1 | What was planned? |
| --- | --- |

Move all six docks from the legacy WMS to the new system in one weekend. Freeze Friday 18:00, go live Sunday 18:00, ship Monday's first wave at 06:00 at full volume. Success meant 95% of Monday orders shipped the same day, with no stock errors.

| 2 | What actually happened? |
| --- | --- |

Data migration went well: inventory accuracy came out at 99.8%. Testing ran 3.5 hours late, and the dock hardware check found that label printers at docks 4 and 5 couldn't print the new labels. Go-live slipped to 23:40 Sunday (+5.7 h). Monday shipped 71% of orders same day; full volume returned Wednesday. Catching up cost 92 extra overtime hours and $6,850 in expedited freight.

| 3 | Why was there a difference? |
| --- | --- |

Root cause.  The older Zebra printers at docks 4 and 5 were never in test scope. The test lab had one printer model.

Contributing.  No go/no-go gate before Sunday, so the delay wasn't escalated until 15:00 on Sunday.

Contributing.  Floor training ran three weeks before go-live; most night-shift staff were still unsure on the new scanners.

| 4 | What will we sustain, and what will we improve? |
| --- | --- |

| Action | Type | Owner | Due |
| --- | --- | --- | --- |
| Keep data validation scripts as a standard cutover step | Sustain | R. Okafor | Done |
| Add every printer and scanner model to the test lab | Improve | S. Patel | 31 Oct |
| Go/no-go gates Sat 22:00 and Sun 10:00 in the runbook | Improve | D. Whitcomb | 16 Oct |
| Rollback rule: trigger, decision owner, deadline | Improve | D. Whitcomb | 23 Oct |
| Floor training within 7 days of go-live | Improve | L. Moreno | 7 Nov |

Ground rules used: no blame, rank left at the door, facts before opinions, every action gets one owner and a date. Full action log in the Excel tracker.