## AAR Summary
AFTER ACTION REPORT
WMS cutover weekend · Harbor Point Logistics
Event 9–12 Oct 2026 · Review held 14 Oct · Facilitator: Dana Whitcomb (PMO) · 14 participants
1 | What was planned? |  |  | Report date | 2026-10-17
Switch all six docks from the legacy WMS to the new system over one weekend: freeze Friday 18:00, go live Sunday 18:00, ship Monday's first wave at 06:00 at normal volume.
2 | What actually happened?
# | Milestone | Planned | Actual | Late (h) | Status
1 | Freeze legacy WMS | 2026-10-09 18:00 | 2026-10-09 18:05
2 | Data extract complete | 2026-10-09 23:00 | 2026-10-10 00:40
3 | Data load + validation | 2026-10-10 14:00 | 2026-10-10 15:10
4 | Integration tests (ERP, carriers) | 2026-10-10 22:00 | 2026-10-11 01:30
5 | Dock hardware check | 2026-10-11 10:00 | 2026-10-11 19:20
6 | Go-live decision | 2026-10-11 18:00 | 2026-10-11 23:40
7 | First wave shipped | 2026-10-12 06:00 | 2026-10-12 07:15
| Result measure | Target | Actual | Gap | Better if
| Monday orders shipped same day | 95% | 71% |  | Higher
| Inventory accuracy after migration | 99.5% | 99.8% |  | Higher
| Overtime hours, cutover weekend | 120 | 212 |  | Lower
| Expedited freight to catch up | 0 | 6850 |  | Lower
| Days to full shipping volume | 1 | 3 |  | Lower
3 | Why was there a difference?
| Root cause | Label printer drivers for the older Zebra units at docks 4 and 5 were never in test scope. The test lab had one printer model.
| Contributing | No go/no-go checkpoint before Sunday, so the slip wasn't escalated until 15:00 on Sunday.
| Contributing | Floor training ran 3 weeks before go-live; scanners were new to most of the night shift.
4 | What will we sustain and improve?
| Open actions |  | Full list with owners and due dates on the Actions tab. Sustain: data validation scripts (0 stock errors). Improve: hardware in test scope, go/no-go gates, training within 1 week of go-live.
Overdue
Complete

## Actions
AAR action log · WMS cutover
# | Action | Type | Owner | Priority | Due | Status | Done on | Days late
1 | Keep the data validation scripts as a standard cutover step | Sustain | R. Okafor | Medium | 2026-10-24 | Done | 2026-10-14
2 | Add every printer and scanner model on site to the test lab | Improve | S. Patel | High | 2026-10-31 | In progress
3 | Insert go/no-go gates at Sat 22:00 and Sun 10:00 in the runbook | Improve | D. Whitcomb | High | 2026-10-16 | In progress
4 | Write a rollback decision rule (trigger, who decides, by when) | Improve | D. Whitcomb | High | 2026-10-23 | Not started
5 | Schedule floor training within 7 days of any go-live | Improve | L. Moreno | Medium | 2026-11-07 | Not started
6 | Replace Zebra units at docks 4 and 5 (end of support) | Improve | S. Patel | Medium | 2026-12-15 | Not started
7 | Keep the hourly war-room bridge; stakeholders rated it 4.6/5 | Sustain | D. Whitcomb | Low | 2026-10-17 | Done | 2026-10-14
8 | Brief carriers 48 h ahead of the next cutover | Improve | J. Lindgren | Medium | 2026-10-14 | Not started