## Daily Report
CONSTRUCTION DAILY REPORT | [5 empty] | REPORT NO.
Superintendent's site log · one sheet per working day
PROJECT | GENERAL CONTRACTOR |  | JOB NO. |  | SUPERINTENDENT |  | LOCATION
Harbor View MOB, Phase 2 | Ridgeline Builders Inc. |  | RB-2214 |  | Dana Whitfield |  | 1180 Harbor Blvd, Tacoma WA
REPORT DATE | CONTRACT START | CONTR. DAYS | DAY NO. | DAYS LEFT | TIME ELAPSED | SHIFT
2026-10-14 | 2026-03-02 | 420 |  |  |  | 7:00 am – 3:30 pm
WORKERS ON SITE | MAN-HOURS TODAY |  | HOURS LOST TO DELAYS |  |  | SAFETY (RECORDABLE / FIRST AID / NEAR MISS)
01 WEATHER & SITE CONDITIONS
CONDITIONS – MORNING | CONDITIONS – AFTERNOON |  | LOW °F | HIGH °F | PRECIP. (IN) | WIND | GROUND / SITE
Overcast, light rain | Rain to 1:30 pm, then clearing |  | 48 | 59 | 0.42 | 12 mph SW | Wet, muddy laydown
02 MANPOWER ON SITE | [6 empty] | Man-hours = workers × hours + OT
Trade | Company | Workers | Hours / Worker | OT Hours (total) | Man-Hours | Work Area / Notes
General Conditions | Ridgeline Builders | 4 | 9 | 0 |  | Super, project engineer, 2 laborers
Concrete | Cascade Concrete Co. | 8 | 8 | 6 |  | Level 3 slab, pour 2 of 3
Structural Steel | Northline Steel Erectors | 6 | 8 | 0 |  | Stair 2 stringers & landings
Framing & Drywall | Summit Interiors | 9 | 8 | 0 |  | Level 1 east suite partitions
Electrical | Brightway Electric | 5 | 8 | 4 |  | Level 2 east rough-in
Plumbing | Puget Mechanical | 4 | 8 | 0 |  | Risers in shafts P1–P3
HVAC | Puget Mechanical | 3 | 8 | 0 |  | Level 1 corridor duct mains
TOTAL ON SITE
03 EQUIPMENT | [6 empty] | Utilization = hours used ÷ (used + idle)
Equipment | Owner / Source | Qty | Hours Used | Hours Idle | Utilization | Notes
Tower crane (172 EC-B) | Rental | 1 | 6.5 | 2 |  | Stood down 8:00–10:00 (rain/wind)
Concrete pump, 47 m boom | Cascade Concrete | 1 | 5 | 1 |  | On site 9:30 am – 3:30 pm
Telehandler, 10k lb | Owned | 2 | 9 | 7 |  | One unit idle most of the day
Scissor lift, 26 ft | Rental | 4 | 18 | 14 |  | Level 1 framing & duct
Skid steer | Owned | 1 | 3 | 5 |  | Mud cleanup at laydown
TOTAL EQUIPMENT
04 WORK PERFORMED TODAY
Activity |  | Location |  | Status | % Complete | Notes / Next Step
Placed Level 3 slab, pour 2 (142 CY) |  | Grid C–F / 3–7 |  | Complete | 100% | Wet cure; strip edge forms Fri
Erected Stair 2 stringers & landings |  | Core B, L1–L3 |  | On Track | 60% | Landing L3 tomorrow
Electrical rough-in, east wing |  | Level 2 east |  | On Track | 45% | Wall boxes 80% set
Set plumbing risers |  | Shafts P1–P3 |  | Behind | 30% | Shaft P2 on hold for RFI-087
Metal stud framing, suites 101–108 |  | Level 1 east |  | On Track | 70% | Top track at 104 corrected
Hung HVAC duct mains |  | Level 1 corridor |  | On Track | 55% | Hangers per revised layout
05 MATERIALS DELIVERED
Material | Supplier | Qty | Unit | Ticket / Delivery No. |  | Received By | Storage / Notes
Ready-mix, 5,000 psi | Cascade Ready-Mix | 142 | CY | 88412–88426 |  | J. Ortiz | Pour 2; 6 cylinder sets taken
#5 rebar bundles | Pacific Rebar Supply | 6 | Bundles | PR-30917 |  | J. Ortiz | North laydown, on dunnage
3-5/8" metal studs, 20 ga | Coastline Building Supply | 1200 | EA | CB-55120 |  | M. Chen | Level 1 staging
4" cast iron pipe, 10 ft | Sound Plumbing Supply | 40 | EA | SP-771904 |  | R. Patel | Conex 2
06 DELAYS, ISSUES & RFIs | [6 empty] | Total feeds the Hours Lost card
Type | Description |  |  |  | Hours Lost | Responsible | Status
Weather | Rain and gusts stopped crane picks 8:00–10:00 am |  |  |  | 2 | — | Closed
Inspection | City deck inspection for pour 2 started 45 min late |  |  |  | 0.75 | City of Tacoma | Closed
RFI | RFI-087: riser offset at Shaft P2; awaiting engineer |  |  |  | 1.5 | Architect | Open
TOTAL TIME LOST
07 SAFETY & SITE VISITORS
TOOLBOX TALK TOPIC |  |  |  | ATTENDEES | RECORDABLE | FIRST AID | NEAR MISSES
Working around concrete pumps and boom hazards |  |  |  | 39 | 0 | 1 | 1
Visitor / Inspector | Company / Agency |  | Time In | Time Out | Hours on Site | Purpose / Result
R. Alvarez | City of Tacoma Building Insp. |  | 7:45 | 8:30 |  | Pre-pour deck inspection (passed)
K. Morgan | Owner's representative |  | 14:00 | 15:15 |  | Weekly walkthrough, L1 & L2
T. Nguyen | Sound Testing Lab |  | 9:30 | 13:00 |  | Slump, air & cylinders, pour 2
08 LOOK-AHEAD & SIGN-OFF
Thu Oct 15: strip edge forms and continue wet cure on L3 pour 2; set Stair 2 landing at L3; continue L2 electrical rough-in.
Fri Oct 16: rebar and embeds for L3 pour 3 (grid F–H); city rebar inspection requested for 10:00 am; scissor lift #4 off-rent.
PREPARED BY | SIGNATURE |  |  | REVIEWED BY (PM) |  |  | DATE SUBMITTED
Dana Whitfield, Superintendent |  |  |  | Marcus Lee, Project Manager
How to use: type over any white cell. Shaded cells and the cards at the top calculate automatically. Copy this sheet for each working day (right-click the tab › Move or Copy › Create a copy).

## Monthly Log
DAILY REPORT LOG · OCTOBER 2026
One line per working day. The last row pulls today's numbers straight from the Daily Report sheet.
Date | Day | Report No. | Workers | Man-Hours | Weather | Hours Lost | Safety Events | Key Activity / Milestone
2026-10-01 |  |  | 34 | 280 | Cloudy, 55°F | 0 | 0 | L3 deck rebar placement
2026-10-02 |  |  | 36 | 296 | Sunny, 61°F | 0 | 0 | L3 slab pour 1 (128 CY)
2026-10-05 |  |  | 31 | 252 | Rain, 52°F | 3.5 | 0 | Interior framing only
2026-10-06 |  |  | 35 | 288 | Showers, 54°F | 1 | 0 | Stair 2 steel delivered
2026-10-07 |  |  | 37 | 304 | Cloudy, 57°F | 0 | 1 | L2 electrical rough-in
2026-10-08 |  |  | 38 | 312 | Sunny, 60°F | 0 | 0 | L3 pour 2 deck prep
2026-10-09 |  |  | 33 | 268 | Sunny, 63°F | 0 | 0 | Rebar inspection, pour 2
2026-10-12 |  |  | 36 | 292 | Cloudy, 58°F | 0.5 | 0 | Plumbing risers started
2026-10-13 |  |  | 38 | 310 | Cloudy, 56°F | 0 | 0 | Pump & pour logistics
MONTH TO DATE
DAILY AVERAGE
PEAK CREW |  |  |  |  | HRS PER WORKER-DAY |  | ← man-hours ÷ worker-days (Workers total)
Formulas:
Report No. = NETWORKDAYS('Daily Report'!$B8,[Date])