| DAILY SITE REPORT Harbor View Medical Office Building, Phase 2 Ridgeline Builders Inc. · Job RB-2214 · 1180 Harbor Blvd, Tacoma WA | REPORT No. 163 Wednesday, Oct 14, 2026 |
| --- | --- |

| SUPERINTENDENT | SHIFT | DAY OF CONTRACT | DAYS REMAINING |
| --- | --- | --- | --- |
| Dana Whitfield | 7:00 am – 3:30 pm | 227 of 420 | 193 (54% elapsed) |

Today in brief.  Level 3 slab pour 2 was placed and finished (142 CY) after a two-hour rain stand-down on the tower crane. 39 workers from 7 trades logged 326 man-hours. Plumbing risers in Shaft P2 remain on hold pending a response to RFI-087. One first-aid case (minor hand laceration, treated on site) and one near miss were recorded; no lost-time injuries.

| 39 | 326 | 4.25 | 0 |
| --- | --- | --- | --- |
| WORKERS ON SITE 7 trades / subs | MAN-HOURS avg 8.4 hrs / worker | HOURS LOST weather, inspection, RFI | RECORDABLES 1 first aid · 1 near miss |

01  Weather & Site Conditions

| MORNING | AFTERNOON | LOW / HIGH | PRECIPITATION | WIND | GROUND |
| --- | --- | --- | --- | --- | --- |
| Overcast, light rain | Rain to 1:30 pm, then clearing | 48°F / 59°F | 0.42 in | 12 mph SW | Wet, muddy laydown |

02  Work Completed Today

| ACTIVITY | LOCATION | STATUS | % DONE | NOTES / NEXT STEP |
| --- | --- | --- | --- | --- |
| Placed Level 3 slab, pour 2 (142 CY) | Grid C–F / 3–7 | Complete | 100% | Wet cure; strip edge forms Fri |
| Erected Stair 2 stringers & landings | Core B, L1–L3 | On Track | 60% | Landing L3 tomorrow |
| Electrical rough-in, east wing | Level 2 east | On Track | 45% | Wall boxes 80% set |
| Set plumbing risers | Shafts P1–P3 | Behind | 30% | Shaft P2 on hold for RFI-087 |
| Metal stud framing, suites 101–108 | Level 1 east | On Track | 70% | Top track at 104 corrected |
| Hung HVAC duct mains | Level 1 corridor | On Track | 55% | Hangers per revised layout |

03  Manpower on Site   man-hours = workers × hours + overtime

| TRADE | COMPANY | WORKERS | HRS EACH | OT HRS | MAN-HOURS |
| --- | --- | --- | --- | --- | --- |
| General Conditions | Ridgeline Builders | 4 | 9 | – | 36 |
| Concrete | Cascade Concrete Co. | 8 | 8 | 6 | 70 |
| Structural Steel | Northline Steel Erectors | 6 | 8 | – | 48 |
| Framing & Drywall | Summit Interiors | 9 | 8 | – | 72 |
| Electrical | Brightway Electric | 5 | 8 | 4 | 44 |
| Plumbing | Puget Mechanical | 4 | 8 | – | 32 |
| HVAC | Puget Mechanical | 3 | 8 | – | 24 |
| Total | 7 trades | 39 |  | 10 | 326 |

04  Equipment

| EQUIPMENT | SOURCE | QTY | USED | IDLE | UTILIZATION |
| --- | --- | --- | --- | --- | --- |
| Tower crane (172 EC-B) | Rental | 1 | 6.5 | 2.0 | 76% |
| Concrete pump, 47 m boom | Cascade Concrete | 1 | 5.0 | 1.0 | 83% |
| Telehandler, 10k lb | Owned | 2 | 9.0 | 7.0 | 56% |
| Scissor lift, 26 ft | Rental | 4 | 18.0 | 14.0 | 56% |
| Skid steer | Owned | 1 | 3.0 | 5.0 | 38% |
| Total |  | 9 | 41.5 | 29.0 | 59% |

05  Materials Delivered

| MATERIAL | SUPPLIER | QTY | TICKET NO. | RECEIVED BY |
| --- | --- | --- | --- | --- |
| Ready-mix, 5,000 psi | Cascade Ready-Mix | 142 CY | 88412–88426 | J. Ortiz |
| #5 rebar bundles | Pacific Rebar Supply | 6 Bundles | PR-30917 | J. Ortiz |
| 3-5/8" metal studs, 20 ga | Coastline Building Supply | 1,200 EA | CB-55120 | M. Chen |
| 4" cast iron pipe, 10 ft | Sound Plumbing Supply | 40 EA | SP-771904 | R. Patel |

06  Delays, Issues & Open RFIs

| TYPE | WHAT HAPPENED | HRS LOST | RESPONSIBLE | STATUS |
| --- | --- | --- | --- | --- |
| Weather | Rain and gusts stopped crane picks 8:00–10:00 am | 2.00 | — | Closed |
| Inspection | City deck inspection for pour 2 started 45 min late | 0.75 | City of Tacoma | Closed |
| RFI | RFI-087: riser offset at Shaft P2; awaiting engineer | 1.50 | Architect | Open |
| Total | 3 items, 1 still open | 4.25 |  |  |

07  Safety & Visitors

Toolbox talk: “Working around concrete pumps and boom hazards” – 39 attendees (matches headcount).

First aid: Summit Interiors framer, minor hand laceration from stud edge; cleaned and bandaged on site, returned to work. Gloves re-issued to crew.

Near miss: unsecured bundle on telehandler forks at north laydown. Load stopped and strapped; operator re-briefed on securing loads.

| VISITOR | COMPANY / AGENCY | ON SITE | PURPOSE / RESULT |
| --- | --- | --- | --- |
| R. Alvarez | City of Tacoma Building Insp. | 7:45 AM – 8:30 AM | Pre-pour deck inspection (passed) |
| K. Morgan | Owner's representative | 2:00 PM – 3:15 PM | Weekly walkthrough, L1 & L2 |
| T. Nguyen | Sound Testing Lab | 9:30 AM – 1:00 PM | Slump, air & cylinders, pour 2 |

08  Look-Ahead (Next Two Working Days)

Thu Oct 15: strip edge forms and continue wet cure on L3 pour 2; set Stair 2 landing at L3; continue L2 electrical rough-in.

Fri Oct 16: rebar and embeds for L3 pour 3 (grid F–H); city rebar inspection requested for 10:00 am; scissor lift #4 off-rent.

| PREPARED BY | REVIEWED BY | DISTRIBUTED TO |
| --- | --- | --- |
| Dana Whitfield, Superintendent | Marcus Lee, Project Manager | Owner's rep · Architect · Project file |

09  Photo Log   replace each box with a dated site photo

| [ insert photo ] | [ insert photo ] |
| --- | --- |
| Photo 1 – L3 pour 2, screed and finish at grid D/5 (10:40 am) | Photo 2 – Stair 2 stringers and L2 landing, Core B |
| [ insert photo ] | [ insert photo ] |
| Photo 3 – Shaft P2 riser offset referenced in RFI-087 | Photo 4 – North laydown after rain; rebar on dunnage |