BUDGET REPORT Department / Project Budget Review • Spend, Variance, Forecast & Approval

1. REPORT DETAILS

| Department / Project | Marketing Department | Budget Period | FY 2026 (Jan–Dec) |
| --- | --- | --- | --- |
| Budget Owner | Name, Designation | Report Period | Q3 2026 (Jul–Sep) |
| Prepared By | Name, Finance | Report Date | 10/10/2026 |

2. BUDGET SUMMARY

| Approved Annual Budget | $250,000 | Spent to Date (Actual) | $171,400 |
| --- | --- | --- | --- |
| Committed (POs / Contracts) | $22,600 | Remaining Budget | $56,000 |
| % of Budget Used | 77.6% | % of Year Elapsed | 75.0% |

3. BUDGET VS ACTUAL BY CATEGORY

| Category | Approved Budget | Actual to Date | Variance | % Used | Comments |
| --- | --- | --- | --- | --- | --- |
| Digital Advertising | $90,000 | $71,300 | $18,700 | 79% | On plan |
| Events & Trade Shows | $45,000 | $41,800 | $3,200 | 93% | Q4 event still to come |
| Content & Design | $35,000 | $24,100 | $10,900 | 69% | Agency invoice pending |
| Salaries (Contract) | $60,000 | $27,500 | $32,500 | 46% | Vacancy since June |
| Software & Tools | $20,000 | $6,700 | $13,300 | 34% | Annual renewals in Nov |

4. SIGNIFICANT VARIANCES – EXPLANATION & ACTION

| Item | Variance | Reason | Action / Decision | Owner |
| --- | --- | --- | --- | --- |
| Events & Trade Shows | +$3,200 at risk | Booth costs 15% above quote | Negotiate Q4 package; cap at $48k | Events Lead |

5. FORECAST TO YEAR END

| Category | Annual Budget | Year-End Forecast | Expected Variance | Notes |
| --- | --- | --- | --- | --- |

6. BUDGET TRANSFERS / CHANGE REQUESTS

| From Category | To Category | Amount | Reason | Approved (Y/N) |
| --- | --- | --- | --- | --- |

7. APPROVAL

| Prepared By | Reviewed By (Finance) | Approved By |
| --- | --- | --- |
| Name: Signature: Date: | Name: Signature: Date: | Name: Signature: Date: |