## Site Visit Log
SITE VISIT REPORT & ACTION TRACKER
Project / Client: |  | Project Name |  |  | Visit Date: | 02/10/2026
Site Address: |  | Street, City |  |  | Visited By: | Name / Role
Purpose of Visit: |  | Progress review / Client meeting |  |  | Weather: | Sunny, 31°C
ATTENDEES
Name |  | Company |  | Role |  | Contact
OBSERVATIONS & ACTION ITEMS
# | Area / Location | Observation | Category | Priority | Action Required | Responsible | Due Date | Status | Overdue?
1 | Block A - Ground Floor | Formwork for columns C4-C7 completed | Progress | Low | Proceed with rebar inspection | Site Engineer | 2026-10-05 | Open
2 | Main Gate | Workers without hard hats near loading area | Safety | High | Toolbox talk; enforce PPE checks | HSE Officer | 2026-10-03 | In Progress
3 | Block B - Roof | Waterproofing membrane joints lifting | Quality | Medium | Re-seal joints and re-test | Subcontractor | 2026-10-08 | Open
4 | Storage Yard | Cement bags stored on bare ground | Quality | Medium | Store on pallets and cover | Storekeeper | 2026-10-04 | Closed
5
6
7
8
9
10
11
12
SUMMARY
Total Observations |  |  |  | Overall Site Condition: |  | Satisfactory
High Priority |  |  |  | Next Visit Date:
Open / In Progress
Closed
Visitor Signature: ____________________ Site Representative: ____________________ Date: __________
Formulas:
Overdue? = IF(OR([Due Date]="",[Status]="Closed"),"",IF([Due Date]<TODAY(),"OVERDUE","On Track"))